## Feuil1
|  | Guillaume | Méliana | Arthur | Total
Week 1 |  |  |  |  | 615 | 945
| Form team, decide on roles. | 5 | 5 | 5
| Form the list of features needed in the sprint backlog. | 60 | 60 | 60
| Create a set of tasks needed to complete the project | 60 | 60 | 60
| Estimate the time needed for each task (in blocks of 1hr, 2hr, 4hr, 8hr, 2Days) | 0 | 0 | 60
| Design the first draft of the UML diagram/model | 0 | 120 | 0
| Get the example code working | 60 | 0 | 0
Week 2 |  |  |  |  | 480 | 465
| Finalise the UML model | 0 | 120 | 0
| Start working on the code prototype based on the example code | 60 | 60 | 60
| Start devising unit tests | 60 | 60 | 60
| Generate working examples of QR codes and directions from reception | 0 | 0 | 0
Week 3 |  |  |  |  | 330 | 135
| work on the code prototype based on the example code | 60 | 60 | 60
| run unit tests | 30 | 0 | 0
| Generate working examples of QR codes and consider timing data from reception | 120 | 0 | 0
Week 4 |  |  |  |  | 30 | 105
| Run unit tests | 30 | 0 | 0
| Add any extra features | 0 | 0 | 0
| Perform dry run of demo | 0 | 0 | 0
Week 5 |  |  |  |  | 105 | 0
| Ensure all deliverables (above) have been submitted. | 0 | 0 | 0
| Commit project to github | 60 | 0 | 0
| Demo project in lab time | 15 | 15 | 15
| Celebrate! | 1 weekend | 1 weekend | 1 weekend | 1560